## Sheet1
Sl.No | Tasks | Priority | Category | Ask | Status
1 | data not getting updated on server | High | Discovery | Execute
2 | Issue Tracker 2K (11 issues) | Medium | Discovery | Execute
3 | Issue Tracker 59 | Medium | Discovery | Execute
4 | Foundation Data (ServiceNow to Eracent) | Very High | Foundation | Devp asap
5 | Technical Design for Data Migration from ADB to Eracent (Asset Data Base) | High | Lifecycle | Load Asset data from Remedy to Eracent,
6 | HAM Catalog items 3000 + devices unique models for catalog creation, list received, Part number and product number to come from the manufacturer | Medium | Lifecycle | Load into Eracent
7 | Workflow reviews with Kiran for Contracts (UAT) | High | Lifecycle | Demo it to Kiran
8 | HAM Process Definition (Attribute process and template) | High | Lifecycle | Define the Processes
9 | Upload templates for HAM processes | High | Lifecycle | Template provided by CG
10 | Americas HAM Process from Ingram | Medium | Lifecycle | To integrate with Ingram
11 | SAM Process Definition (Attribute process and template) | High | Lifecycle | Define the Processes
12 | SAM Catalog Items | High | Lifecycle | Load into Eracent

## Sheet2
Name of the Meeting | Text Field
Agenda | Text Field
Attendees | Text Field
Sl.No | Discussion Item | Action Item | Task Desc | Task Goal | Priority | Status | Assigned to | Planned Completion Date | Planned Start Date
1 | Leave Tracker | Develop technical document with
Seq No | Integration Name | Integration classification | Inbound / Outbound | From System | To System | Stream | Integration Method | Frequency | Requirement\activity | Comments | Tool\applications Link | Priority | Status | Comments | Region | Eracent Technical details | 3rd party system technical details | Prod | UAT | entry | Task | Validation | Exit
Sl.No | Requirement Description | Stream | Fullfillment | Status | Approved by | Start Date | End Date