## Sheet1
Sl.No | Defect Description | Records | Action | Assigned to | Status
1 | Create records that did not have category | 1250 | Provide Category in View | Sachin | Work In Progress
2 | First Name, Last Name and email id | 43326 | Sachin to provide User data | Sachin | Work In Progress
3 | AD_User id has -, = and other junk charcaters | 21368 | data to be populated in view | Sachin | Work In Progress
4 | Status as Blank | 18 | data to be populated in view | Sachin | Work In Progress
5 | Same Serial numbers with two recon id | 187 | To have unique serial number while pulling data | Vamshi | Work In Progress
6 | Allocation Date not mapped | 1531 | Allocation date is mapped to Status Change Date | Vamshi | Completed
7 | Remarks has to map to all the HAM Categories |  |  |  | Completed