## Sheet2
HAM Activities
Sl.No | Task Description & Exit Criteria | Inputs from CG | Migrate to Dev | Status in Dev | Migrated to Prod | Start Date | Completion Date
1 | Status & Status Reason |  | Need to Check with Dev team | Pending | Pending
2 | Mandatory Field based on Condition |  | Need to Check with Dev team | Pending | Pending
3 | Mandatory Field without Condition |  | Move to Dev from POC | Pending | Pending
4 | List of Values from POC to Dev to Prod |  | Yes | Pending | Pending
5 | Asset Status Synch |  |  | Pending | Pending
6 | HAM Team Role (Cannot add LOVs) |  |  | Pending | Pending
7 | HAM Security Role (Cannot Add categories etc) |  |  | Pending | Pending
8 | BMC Integration |  | Pending in Dev | Pending | Pending
9 | Export of HAM data |  | Complete | in Testing | Pending
10 | Catalog Items from ITPedia |  |  |  | Pending
11 | Category mapping for Itpedia Import for HAM Categories |  | Pending in Dev | Pending | Pending
12 | XML PO Extract for Cloudblue |  | Pending in Dev |  | Pending
13 | XML Asset Updation Import |  | March 23, 2020 |  | Pending
14 | XML Asset Creation Import |  | March 23, 2020 |  | Pending
15 | GRN Process |  | Validate Process with Xls uplaod |  | Pending
16 | Disposal Process & Disposal Location |  |  |  | Pending
17 | Non Serialized Inventory (IMAC Processes) | Rajul to Provide Stock Room Processes, Minimum Qty, Reorder Aty, Define Stock Room |  |  | Pending
18 | Company, Groups & Organization Definition |  |  |  | Pending
19 | Bulk Uplaod Templates (xls sheets) & Procedure |  |  |  | Pending
20 | Bulk Asset Creation Templates (xls sheets) & Procedure |  |  |  | Pending
21 | Process Documentation (xls sheet) | Process Flow Chart | Exisitng | Exisiting | Exisiting
22 | Procedure Documentation | Execution on tool |  |  | Pending
23 | HAM Trainings Sessions LC |  |  |  | Pending
24 | Workflow Migration |  | Pending | Pending | Pending
25 | UAT Sign Off |  |  |  |  | Target 30 March