## ham
HAM Activities
Sl.No | Track | Sub Track | Task Description & Exit Criteria | Inputs from CG | Migrate to Dev | Status in Dev | Migrated to Prod | Start Date | Completion Date
1 | HAM |  | Status & Status Reason |  | Need to Check with Dev team | Pending | Pending
2 | HAM |  | Mandatory Field based on Condition |  | Need to Check with Dev team | Pending | Pending
3 | HAM |  | Mandatory Field without Condition |  | Move to Dev from POC | Pending | Pending
4 | HAM |  | List of Values from POC to Dev to Prod |  | Yes | Pending | Pending
5 | HAM |  | Asset Status Synch |  |  | Pending | Pending
6 | HAM |  | HAM Team Role (Cannot add LOVs) |  |  | Pending | Pending
7 | HAM |  | HAM Security Role (Cannot Add categories etc) |  |  | Pending | Pending
8 | HAM | Integration | BMC Integration |  | Pending in Dev | Pending | Pending
9 | HAM | Reporting | Export of HAM data |  | Complete | in Testing | Pending
10 | HAM |  | Catalog Items from ITPedia |  |  |  | Pending
11 | HAM |  | Category mapping for Itpedia Import for HAM Categories |  | Pending in Dev | Pending | Pending
12 | HAM | Integration | XML PO Extract for Cloudblue |  | Pending in Dev |  | Pending
13 | HAM | Integration | XML Asset Updation Import |  | March 23, 2020 |  | Pending
14 | HAM | Integration | XML Asset Creation Import |  | March 23, 2020 |  | Pending
15 | HAM |  | GRN Process |  | Validate Process with Xls uplaod |  | Pending
16 | HAM |  | Disposal Process & Disposal Location |  |  |  | Pending
17 | HAM |  | Non Serialized Inventory (IMAC Processes) | Rajul to Provide Stock Room Processes, Minimum Qty, Reorder Aty, Define Stock Room |  |  | Pending
18 | HAM |  | Company, Groups & Organization Definition |  |  |  | Pending
19 | HAM |  | Bulk Uplaod Templates (xls sheets) & Procedure |  |  |  | Pending
20 | HAM |  | Bulk Asset Creation Templates (xls sheets) & Procedure |  |  |  | Pending
21 | HAM |  | Process Documentation (xls sheet) | Process Flow Chart | Exisitng | Exisiting | Exisiting
22 | HAM |  | Procedure Documentation | Execution on tool |  |  | Pending
23 | HAM |  | HAM Trainings Sessions LC |  |  |  | Pending
24 | HAM |  | Workflow Migration |  | Pending | Pending | Pending
25 | HAM |  | UAT Sign Off |  |  |  |  | Target 30 March
26 | Foundation | Integration | User data
27 | Foundation | Integration | Location
28 | Foundation | Integration | Legal Entity Data
29 | Foundation | Integration | Organization Data
30 | Foundation | Integration | Assignment Data
31 | Foundation | Integration | Cost Centers
32 | Foundation | Supplier | Supplier Data
33 | Discovery | Collection | Collection Stats
34 | Discovery | Rules | Rules for Network Devices
35 | Discovery | Rules | Report of Devices without Serial Number
36 | Discovery | Reporting | Report of Unidentified Devices in Asset Discovery & Network Discovery
37 | Discovery | Reporting | SSH for Stack Switches Discovery
| Discovery | Recon | Finding Missing devices in Discovery & which are deployed in LC and Vice versa